## Priority 1
SEND Joint Local Area Action Plan
Priority 1: Know our local area and effectively plan for the needs of our children, young people and families | [9 empty] | RAG Rating: Blue: Action has been delivered Green: In delivery and timeline on track Amber: In delivery but delays / uncertainty over future delivery. Red: Work not yet commenced, budget not yet allocated and future delivery at risk or unknown. Impact: High - Significant impact on CYP outcomes or budget Medium – Moderate impact on CYP outcomes or budget Low - Limited impact on CYP outcomes or budget Timeframe (short-term/ medium-term/ long-term) Short-term - (delivery/ completion in under 1 year) Medium-term - (delivery/ completion within 1 - 3 years) Long-term - (delivery/ completion in 3 - 5 years) |  |  |  |  | Ofsted and CQC Proposed Inspection Outcomes (TBC live consultation) https://www.gov.uk/government/consultations/a-new-approach-to-area-send-inspections OIF 1: children and young people’s needs are identified accurately and assessed in a timely and effective way OIF 2: children, young people and their families participate in decision-making about their individual plans and support OIF 3: children and young people receive the right help at the right time OIF 4: children and young people are well prepared for their next steps, and achieve strong outcomes OIF 5: children and young people with SEND are valued, visible and included in their communities
Identified aims of the SEN Self Evaluation Framework (SEF): 1. A developed and agreed joint commissioning action plan with CCG, LA and Health to meet the needs of children and young people with SEN; Strategic Improvements Required
Objective Code | Objective / Commitment 2022-26 | Post Area SEND Inspection: Area of Improvement & Judgement | Post Area SEND Inspection: Objective | Action Sub-Code | Actions | Measure/ SEN2 Indicator | Progress update | Education Phase | Education, Health or Social Care | Lead (name, title and org) | Delegated officer (delivery) | Timeframe (short- term/ medium-term/ long-term) | Deadline/ expected by | RAG Rating | Potential OIF Code Click here for more information | Impact | High, medium or Low Impact | Risk Register Listing
1.1 | Develop our services based on high quality data and knowledge, that respond to the changing needs of our diverse community, their lived experiences, and the performance of our local area. |  |  | 1.1a | Develop a SEND Data Dashboard that can inform on services, that is regularly updated with information from all partners and a Dashboard that is issued monthly and termly to the partnership | An approved SEND Board Dashboard is agreed. | There is a SEN Dashboard developed for the SEND Board. and a strategic SEN Dashboard that sets out all current performance. September 2023 | All | All | Head of SEN and Curriculum Inclusion | High Needs and Tracking Manager | Medium Term | Spring 2023 |  | 1, 2, 3, 4 & 5 | The SEND board will have strategic oversight of strengths, opportunities and weaknesses and challenges | High | no
1.2 | Carry out ongoing analysis to identify local trends to help us to better plan and secure services and support for the future. |  |  | 1.2a | All Services to contribute to the design and development of services to better plan and secure services. All commissioned services to develop and provide annual reports (to a standardised format) to provide trend analysis. | Tracking of: Case Studies , SEN Panel Decisions, Provision and Placement Panel Decisions, Feedback from SENCO Conferences; Develop a Report Template | A Case Study process is in design to support better outcomes for CYP, Placement and Provision Panel is in place and trends are identified, the SEN Panel reviews its decisions to shape support to SENCOs and the wider offer to children and families, SENCO Coffee mornings occur monthly with the Head of SEN and SEN Manager to support analysis of performance. | All | All | Principle Educational Psychology and Strategic Mental Health Lead | Head of SEN and Curriculum Inclusion | Medium Term | 2024-03-01 |  | 1 & 2 | Services will be better prepared to manage complex cases. CYP will have the right support that will enable them to make progress, based on the findings of case-studies | High | yes
1.3 | Extend the range of opportunities to work in partnership with children, young people and their families to influence and shape services and support in Enfield. This includes through consultation, engagement and co-production that is meaningful to our children, young people and families. |  |  | 1.3a | Parents and children/young people to participate in activities that support the development of the SEND Partnership and respective services | Families will be fully involved in shaping the service offer. | All EHCPs are Co produced, Our Voice attend Operational development meetings for SEN, Our Voice Conferences are attended and Our Voice Summer and Winter fairs have recently been attended by SEN and Social Care. Transition meetings are attended by parents/carers. Our Voice are part of Heads of Service Catch up on a monthly basis and attend SEN recruitment interviews. Our Voice attend the SEND Partnership Board and a range of other partnership meetings and workstreams. | All | All | HoS For each area | Head of SEN and Curriculum Inclusion | Medium Term | Autumn 2023 |  | 1, 2, 3, 4 & 5 | Parents and stakeholders will be able to shape the SEND offer | High | no
1.4 | Continually evaluate the impact and performance of our services, to make sure we effectively use our resources to have the greatest impact. This includes services we provide ourselves across the SEND Partnership, and services we commission other organisations to deliver. |  |  | 1.4a | Identified SEND partnership teams/services across Education, Health and Social Care to produce an annual report (to a standardised format) that is submitted to the SEND Partnership that provides a clear account of trends and analyses of service issues. | A annual report is produced for the SEND Board that will support commissioning arrangements. | N/A | All | All | Head of Commissioning – CYP and Public Health | Service Development Manager - SEND | Medium Term | Summer 2023 |  | 1, 2, 3, 4 & 5 | The SEND board will have oversight of key trends that will support with the annual commissioning decisions and structure. | High | yes
|  |  |  | 1.4b | Develop a SEND Health Action Plan | An Action Plan is developed and consulted upon with the SEND Partnership. | A SEND Health Action plan has been agreed by the SEND Board. | All | Health | Assistant Director, Start Well (CYP Joint Commissioning) Islington - seconded | TBC | Short Term | Spring 2023 |  | 1, 2, 3, 4 & 5 | Health will identify areas of development in a similar format to the SEND action plan. The SEND partnership board will have oversight of key developments in line with overall SEND strategy. | High | no
|  |  |  | 1.4c | Review of the Emotional Wellbeing and Mental Health in Schools Offer to be undertaken | Annual Health and Wellbeing school survey to be undertaken, analysed, reported and action taken. A full review to be completed with a report with recommendations. This will be carried out with key partners and schools. | 2020/21 Health and Wellbeing school survey was developed and sent to schools in June 2021. 39% return. The findings were reported through the Anna Freud link programme. Actions to be followed up with the CYP Mental Health partnership. CYP Mental Health partnership group to be established with Health colleagues. An interim mapping exercise has been undertaken and is now with the ICB for further update. | All | Education, Health, Social Care (Early Help) | Principle Educational Psychology and Strategic Mental Health Lead (Emotional Wellbeing/Mental Health) - lead, Head of Service for Young People and Community Safety, Head of Commissioning – CYP and Public Health (LA Comm), CAMHS & Integrated Partnership Commissioning Manager | Principle Educational Psychology and Strategic Mental Health Lead | Medium Term | Spring 2024 |  | 1, 2, 3, 4 & 5 | Any gaps in provision will be identified and collective plans to address these gaps will be developed so that children and young people have accessible support within the school context. | Medium | yes
|  |  |  | 1.4d | Commission a parent/carer survey specifically on access, impact and outcomes. | Survey timeframe and implementation with Our Voice | N/A | All | Education, Health, Social Care (Early Help) | TBC | TBC | Short Term | Spring 2023 |  | 1, 2, 3, 4 & 5 | Children , young people and parents/carers will have the opportunity to share their views and feed into a service which impacts them. | High | no
|  |  |  | 1.4e | Continue to develop Evaluation of EHC Needs Assessment and Annual Review Feedback | A Evaluation template is complete and reviewed. | An evaluation template has been used but insufficient results achieved to date. Template is being reviewed for September 2022/23 academic year | All | All | SEN Service Manager | SEN Review & Transfer Team Manager | Short Term | Summer 22 |  | 1, 2, 3, 4 & 5 | Parents are able to provide insight into the experience of the EHC Needs Assessment and Annual Review process, so that standards are high and meet the needs of CYP with SEN. | High | no
|  |  |  | 1.4f | Develop a post 14 tracking report to identify trends and analysis of performance and outcomes for young people. | A Tracking System is in place and embedded so that all outcomes can be achieved: This includes, tracking of outcomes, tracking sheet to providers and social care delivery agencies | There is a Cross Agencies tracking of outcomes at key transition phases, careers and through a recently established PFA group. | All | All | SEN Service Manager | High Needs and Tracking Manager | Short Term | Spring 2023 |  | 2, 3, 4 & 5 | This will ensure that young people have the right options at the right time and are well prepared for their next steps. | High | no
|  |  |  | 1.4g | Participate in Our Voice Annual Conference at parent events across the year | Utilise Our Voice Conference Feedback to establish service weaknesses | Conferences are attended | All | All | Head of SEN and Curriculum Inclusion | SEN Service Manager | Medium Term | Autumn 2023 |  | 1, 2, 3, 4 & 5 | Families will be able to fully contribute to the shaping of services to better meet their children's needs | Medium | no
|  |  |  | 1.4h | Gain the views of young people to inform on service delivery. | Need to put in "All about us" | Views were gained on SEN operational documentation and this resulted in a new EHCP template. | All | All | HOS - SEND Transition Manager | SEND Improvement Lead | Medium Term | Autumn 2023 |  | 1, 2, 3, 4 & 5 | To create a service which is in collaboration with young people in the community that it serves. Ensuring their views feed into service developments and delivery. | High | yes
|  |  |  | 1.4i | Utilise the Quality Assurance Framework to continually improve the experience of CYP and work-force development | Continue To refine the QA process and feedback to the SEND Board. | A QA Process is in place but requires more embedding with Annual Reviews and with Director level Dip-sampling. | All | All | Send Improvement Lead | SEN Manager | Medium Term | Autumn 2023 |  | 1, 2, 3, 4 & 5 | CYP will have higher quality plans with clear outcomes that prepare them for their next steps | Medium | no
1.5 | Develop and agree a shared SEND Partnership outcome framework. The outcome framework will link the work and the impact of services and support across education, health and social care with the everyday life outcomes we want for our children and young people. |  |  | 1.5a | SEN Partnership to scope the development of an outcomes framework (similar to Hertfordshire Outcome Bees) that is aligned with the PfA outcomes. This will have agreed overarching outcomes with subcategory indicators that all partners can align the productivity, performance and impact of their teams to. https://www.hertfordshire.gov.uk/services/childrens-social-care/child-protection/hertfordshire-safeguarding-children-partnership/professionals-and-volunteers/hertfordshires-6-outcome-bees.aspx | An outcomes framework has been co-produced, published and is being actively used. | Annual Reviews Take Place and there is some evidence of outcomes captured at key stages of education., School improvement also capture the performance of pupils with EHCPs and those on SEN Support. An Outcomes Framework will be developed in line with the Children and Families Act, SEND Code of Practise and the OFSTED Framework. | All | All | Head of Commissioning – CYP and Public Health | SEND Improvement Lead | Medium Term | Autumn 2024 |  | 1, 2, 3, 4 & 5 | CYP will have softer outcomes tracked alongside their key phase academic outcomes. | High | yes
1.6 |  | Parents and carers are typically not consulted by speech and language therapists when they are commissioned to complete a statutory assessment of a child or young person’s needs. This limits the information available when making decisions about how speech and language needs of children and young people with SEND can best be met. | Facilitate discussions with our partners to secure opportunities for families to be involved in speech and language assessments | 1.6a | Work in partnership with our health partners to agree opportunities for parental engagement as part of the statutory assessment. This work will also include reviewing current commissioning arrangements | SEND Board | Parents have been receiving three hours of support to discuss the content of the EHCP and the ongoing delivery of that content. Discussions have taken place with commissioner (13 Sept) to review the commissioning of speech and language. 2 x FTE therapists have been recruited to support the Statutory assessment. DBV will review the process as part of the agreed programme of works | All | Heath | SEN Commissioner, DCO, Joint Care Group Manager: School Age Speech and Language Services and SLT Clinical Leads, CYP Community Service Manager |  | Medium Term | 2024-03-01 |  | 2,3,4,5 | The statutory assessment will be informed by parent/carers knowledge, which will benefit the identification and delivery of Speech and Language support. | Medium | no
1.7 |  | Currently, there is very limited residential respite care providing overnight stays to those families needing a high level of support. Leaders have recognised this, and development of a residential short breaks provision is in the early stages of planning. | Work with children, young people and families to understand the current respite needs of our families and identify opportunities to extend the current offer. | 1.7a | Carry out bespoke engagement with children, young people and families to identify and quantify their current needs concerning overnight stays. Utilise this information to inform the development of short breaks provision planning. | Quarterly progress updates to the SEND Board | JSDC have put in a bid to secure additional funding for short term breaks | All | All | Head of Service for Disabled Children |  | Medium Term | 2024-04-01 |  | 1, 2, 3, 4 & 5 | Children, young people and their families will have access to more respite opportunities |  | no
1.8 |  | Sometimes information from health professionals’ work with children and young people with SEND is not made available to multi-agency partners. It is up to parents and carers to bring this new information about a child or young person’s needs to annual reviews of EHC plans. | Develop our communication systems to make sure that health ,education and social care records are shared in a timely manner and inform SEN Support and EHCP’s. This includes, service transitions details, discharge letters, and updates as to changing needs | 1.8a | Linked to Priority 4.4a |  |  |  | All | Head of SEN and Curriculum Inclusion/DCO | SEN Improvement Lead | Medium Term | 2024-03-01 |  | 1, 2, 3, 4 & 5 | All needs and advices will be captured in the EHCP and subsequent Annual Reviews. | Medium | no

## Priority 2
SEND Joint Local Area Action Plan
Priority 2: Identify needs early and provide the right support, in the right place, at the right time | [9 empty] | RAG Rating: Blue: Action has been delivered Green: In delivery and timeline on track Amber: In delivery but delays / uncertainty over future delivery. Red: Work not yet commenced, budget not yet allocated and future delivery at risk or unknown. Impact: High - Significant impact on CYP outcomes or budget Medium – Moderate impact on CYP outcomes or budget Low - Limited impact on CYP outcomes or budget Timeframe (short-term/ medium-term/ long-term) Short-term - (delivery/ completion in under 1 year) Medium-term - (delivery/ completion within 1 - 3 years) Long-term - (delivery/ completion in 3 - 5 years) |  |  |  |  | Ofsted and CQC Proposed Inspection Outcomes (TBC live consultation) https://www.gov.uk/government/consultations/a-new-approach-to-area-send-inspections OIF 1: children and young people’s needs are identified accurately and assessed in a timely and effective way OIF 2: children, young people and their families participate in decision-making about their individual plans and support OIF 3: children and young people receive the right help at the right time OIF 4: children and young people are well prepared for their next steps, and achieve strong outcomes OIF 5: children and young people with SEND are valued, visible and included in their communities
Identified aims of the SEN Self Evaluation Framework (SEF): 1. The Effectiveness of the Local Area in the Identification of Children and Young People who have Special Educational Needs and/or Disabilities.
Objective Code | Objective / Commitment 2022-26 | Post Area SEND Inspection: Area of Improvement & Judgement | Post Area SEND Inspection: Objective | Action Sub-Code | Actions | Measure/ SEN2 Indicator | Progress update | Education Phase | Education, Health or Social Care | Lead (name, title and org) | Delegated officer (delivery) | Timeframe (short- term/ medium-term/ long-term) | Deadline/ Expected by | RAG Rating | Potential OIF Code Click here for more information | Impact | High, medium or Low Impact | Risk Register Listing
2.1 | Identify SEND early by effectively developing our services, to ensure robust processes and the right workforce skills and knowledge are in place across education, health and social care. |  |  | 2.1a | To improve knowledge, practice and confidence of early years providers in applying for EHC Needs Assessments. | Applications of EHC needs will be of a higher standard | SEN Services Briefing to PVI. Support given individually on request. | Early Years | Education | Early Years SEN Team Manager/Early Years Team Manager | TBC | Medium-term | Spring 2023 |  | 3 & 4 | Settings will fully understand SEN support and the assess, plan, do, review cycle. | Medium | N/A
|  |  |  | 2.1b | Making sure early years providers understand the graduated response and ordinarily available provision. | Training will be provided on ordinarily availble provision. A new OAP will be provided for Early Years | EY SEND Forums cover presenting prioriites. Training package developed. EY OAP document to be developed after School age OAP is completed. | Early Years | Education | Early Years SEN Team Manager | TBC | Short-term | Spring 2023 |  | 1, 3 & 4 | Settings fully understand their responsibility in providing SEN support to early years children. | Low | N/A
|  |  |  | 2.1c | To strengthen the transition process between nursery and reception. | Area SENCOs to support settings with transition to reception and to make sure there is relevant training for settings, and a process for transitions that is followed by PVIs and nurseries. | Transition document reviewed in line with new EYFS. EY SENCO Forum delivered on good transition planning. Brief guidance provided to PVI. ASENCO prioritise transition in the summer term. JH prioritise transiton at EY Team Leaders Forum. | Early Years | Education | Early Years SEN Team Manager/Early Years Team Manager | TBC | Short-term | Spring 2023 |  | 1, 3 & 4 | Children transition is planned and prepared for with their needs met and understood by the future setting in a timely manner to reduce anxiety and stress, and placement breakdown. | Low | N/A
|  |  |  | 2.1d | Develop a process to recruit and retain early years staff. | EY to support settings with recruitment and retention of EY staff, including EY Childcare Career pathways | Free job advert platform (JVB) is available for all PVIs. Recruitment training is offered to all Providers. EY Froum include career pathways, and national qualification training is cascaded to providers. | Early Years | Education | Early Years Team Manager | TBC | Medium-term | Autumn 2023 |  | 1 | All settings will have qualified staff and knowleagable about the children they work with and need in their local area. | Medium | N/A
|  |  |  | 2.1e | Increase early years health visiting assessments of children 8-12 months old. | That all children will receive a health visiting assessment with the ASQ 2 completed. | Take-up in Q1 2022/23 is 62%, up from 53% at the same point last year. This is still below the London average of 68.6%. Service was impacted by Covid and is now returning to face-to-face model, HV recruitment is underway and community clinic space is under review - likely an increase will be required to meet demand | Early Years | Education | Head of Commissioning – CYP and Public Health | Senior Public Health Service Development Manager | Medium-term | Autumn 2023 |  | 1, 2, 3, 4 & 5 | Childrens needs will be identified early and they will receive the right support at the right time, in the right setting and with support from health and social care staff. | High | 4
|  |  |  | 2.1f | Reduce waiting times for neurodevelpmental assessments. | Children will be seen more promptly and will receive the right support for their needs as part of a pre diagnostic pathway so interventions are based on needs not diagnostics. | NLC ICP are currently reviewing the diagnostic assessment process with a range of stakeholders and are in line with parental consultation. Backlog recovery plan 22/23-24 through the assessment hub and Helios , with developing transformational plans, being implemented to reduce waiting times. An Enfield wide project has been reviewed and is developing a transformed neurodiversity pathway. | Early Years | Health | Head of CYP & Family services HEALTH | TBC | Medium-term | Autumn 2024 |  | 1, 2, 3, 4 & 5 | All CYP will receive the right support at the right time, and families and settings will receive support in meeting the needs of CYP. | High | yes
|  |  |  | 2.1g | Clear emotional wellbeing and mental health offer for 0-5 through Children's Centres to make sure parents/carers are supported to effectively attune to and care for their babies and children in the context of additional risk factors, e.g. parental mental health, children with SEN etc) | This needs input from CAMHS, CCs, 0-19 Service (MW/HV). | Children's Centre delivering Being a Parent course on a regular basis, receiving referrals from health and social care. Also hosting EPIP on a regular basis. First Time Parenting course is back face-to-face and regularly delivered, including a MH component. |  | All | Head of Commissioning – CYP and Public Health / Head of CYP & Family services HEALTH / Head of Service:Young People and Community Safety | TBC | Long-term | Autumng 2024 |  | 1, 2, 3, 4 & 5 |  | High | no
|  |  |  | 2.1h.1 | Improve timeliness of advices for EHCNA’s. | All advices from professionals and services to be received within the 6-week statutory time frame. | All school advices are submitted with the EHCNA | All phases | Education | SEN Service Manager | SEN Review & Transfer Team Manager | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 | Quality of plans become variable, SEN staff have to amend plans once more advices are received. Decisions are made on Education advice and 6 and 20 week timelines are impacted upon. Additional pressures are then placed on the Annual Review team when they are subject to amending plans early. | Low | no
|  |  |  | 2.1h.2 |  |  | 74% of EP advice are within 6 week deadline |  | Education | Principle Educational Psychology and Strategic Mental Health Lead | Educational Psychologist | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 |  | Low | no
|  |  |  | 2.1h.3 |  |  | 49% of Speech and Language advice is out of time |  | Health | Head of CYP & Family services HEALTH | Joint Care Group Manager: School Age Speech and Language Services and SLT Clinical Leads | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 |  | Medium | yes
|  |  |  | 2.1h.4 |  |  | 62% OT advice |  | Health | Head of CYP & Family services HEALTH | Childrens Occupational Therapy Clinical Lead | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 |  | Medium | yes
|  |  |  | 2.1h.5 |  |  | 75% of Health advice are out of time |  | Health | Head of CYP & Family services HEALTH | Joint Care Group Manager: School Age Speech and Language Services and SLT Clinical Leads | Short-term | Autumn 2024 |  | 1, 2, 3, 4 & 5 |  | High | yes
|  |  |  | 2.1h.6 |  |  | 75% of CAMHS advices are out of time |  | Health | Head of CYP & Family services HEALTH | TBC | Medium-term | Autumn 2024 |  | 1, 2, 3, 4 & 5 |  | High | yes
|  |  |  | 2.1h.7 |  |  | 37% of Physio Therapy advices are out of time |  | Health | Head of CYP & Family services HEALTH | TBC | Medium-term | Spring 2023 |  | 1, 2, 3, 4 & 5 |  | Low | no
|  |  |  | 2.1h.8 |  |  | 69% of Social Care advices are out of time - new DSCO has been recruited |  | Social Care | Head of Service for disabled children | Designate Social Care Officer | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 |  | Low | no
|  |  |  | 2.1i | The newly developed Enfield Communication Advisory Support Service (ECASS) needs time to embed following its inception in September 2021. | Not all schools are benefiting from the programme at present (Cigdem to add). To integrate a whole offer by including Health provision at Universal and targeted levels with ECASS. | Programme commenced in September 2021 and there are 5 strands. | All phases | Education | Head of SEN and Curriculum Inclusion | ECASS Service Lead & Senior Specialist | Short-term | Autumn 2023 |  | 1, 2, 3, 4 & 5 | Education settings, families and children as a universal offer will have their speech, language and communication needs met | Low | no
|  |  |  | 2.1j | My Young Mind Enfield (MYME) will be expanded to reach all Enfield schools. | 1) The number of CYP accessing Evidence-based interventions for mild to moderate mental health and emotional wellbeing concerns 2) The number of senior mental health leads attending the SMHL Network (and schools represented), attended DfE SMHL accredited training and the number of schools that have completed a whole-school approach to mental health and wellbeing. | There are currently 3 funded Mental Health Support Teams. This has enabled 49 education sites to have been offered MYME support |  | Health | Head of Children and Young People Strategic Commissioning | Clinical Psychologist and MHST Clinical and Team Lead | Long-term | Autumn 2023 |  | 1, 3 | 1) CYP access Evidence-based interventions for mild to moderate mental health and emotional wellbeing concerns 2) senior mental health leads in schools are supported to develop a whole-school approach to mental health and wellbeing. 3) Schools are provided with timely advice and signposting. | Medium | yes
|  |  |  | 2.1k | The Enfield Trauma Informed Practice in Schools & Settings (ETIPSS) initiatives needs to continue to be delivered across schools and be rolled out to early years settings by securing additional funding. E-TIPSS roles out the ARC Framework to support trauma infomred practice delivery. | 1) Number of schools that have engaged with the programme (Central Briefings, ARC Training and Whole School Community Training/Implementation). 2) Number of partners who have attended the training. 3) Number of E-TIPSS Champions trained to support the sustainabilty and growth of the programme across Enfield. 4) E-TIPSS is included in Council strategy documents to support outcomes across the local area. | 1) 70 schools have engaged with ETIPSS programme ( This has include ETIPSS briefing sessions, the centrally organised full two day ARC training. 9 of these schools have had ETIPSS ARC two day training delivered to their whole school staff group and are engaged in the implementation offer). 2) 96 partners across 14 teams have attended the ETIPSS training. 3) There are 22 E-TIPSS Champions trained across 9 teams. 4) Trauma Informed Practice is recommended in Enfield Poverty and Inequality Report. E-TIPSS is referenced in Early Help for All, Fairer Enfield, Tackling Neglect, SEN Strategy & Inclusion Charter. Project Lead and project co-ordinator funded for school roll out (project Lead is currently a vacant post). Additional Funding has been secured to provide training for professionals and for school staff working with LAC and CIN and Early Years. | Primary and Secondary at present | All | Principle Educational Psychology and Strategic Mental Health Lead | Vacant | Long-term | 2026 |  | 1, 3, 4, 5 | Reduction in exclusions, youth violence, restraint practice, use of isolation rooms. Attendance and attainment improves. | Medium | no
|  |  |  | 2.1l | Increase uptake of health visiting assessements | Head of CYP & Family services HEALTH to add |  |  | Health | [7 empty] | High | RL - mark
2.2 | Work together as a partnership to make sure families have access to appropriate information, advice and support for their child’s individual needs and their family circumstances. This includes a well-publicised, up-to-date, easy to understand and navigate Local Offer for SEND, developed in partnership with our parents and carers. NOTE: Wording amended post OFSTED to include transition from children to adult health service and educational settings |  |  | 2.2a | To update the Local Offer to ensure information is up-to date accessible and | Local Offer is updated regularly with accurate information | Launched new website 2022 - peer review undertaken 2022 - service updates 2022 | All phases | Social Care | Head of Service for disabled children | SEND Transition Manager | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 | Parents are unclear of how to raise issues and navigate the system in having their CYPs needs met. | Medium | no
|  |  |  | 2.2b | Collate more feedback from parents/carers as a partnership to improve service delivery | All agencies to provide evaluations of parent/carers feedback regarding service delivery | Monthly catch up with Our Voice occur with Heads of service. Our Voice annual conference attended. Collate parent carer and schools feedback on the Health offer | All phases | Strategic | Head of SEN and Curriculum Inclusion & Head of CYP & Family services HEALTH | No officer required | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 | We don't have full understanding of parental satisfaction with the services on offer. Services are transformed to meet the needs of families and settings. | Low | no
[7 empty] | EHCN evaulation is undertaken but there is insufficient feedback to determine satisfaction | All phases | Education | SEN Service Manager | SEN Review & Transfer Team Manager | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 |  | Low | no
[7 empty] | Satisfaction survey from Health | All phases | Health | Head of CYP & Family services HEALTH | Joint Care Group Manager: School Age Speech and Language Services and SLT Clinical Leads | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 |  | Low | no
[7 empty] | Satisfaction survey from EPS | All phases | Education | Principle Educational Psychology and Strategic Mental Health Lead | Educational Psychologist | Short-term | Spring 2023 |  | 1, 2, 3, 4 & 5 |  | Low | no
|  | Transition to Adult Health Services: Leaders should ensure that children and young people with SEND who move from children to adult health services experience a smooth and effective transition. | To revise the Post 14 Annual Review offer starting from Year 9 for young people who are unlikely to meet adult services thresholds |  | To devise a Post 14 checklist agreed with colleagues within SEN and Adult Health Services to identify pathways for transition or step down | Creation and application of Post 14 checklist for all young people undergoing Annual Reviews at age 14 | A new checklist to be devised to sit alongside Annual Reviews to make certain that SEN officers plan for a smooth transition. | Post 14 | Education | SEN Improvement Lead | SEN Service Manager |  | 2023-12-01 |  |  | All YP will have an updated EHCP with appropriate next steps. |  | no
|  |  | To review the Early Notification Form (ENF) to TOG to make sure that it captures all young people with an EHCP especially those who will require a universal offer |  | To work in partnership to review the current process, identify barriers and agree updates to ensure the system is fit for purpose. | Reviewed and amended ENF with pathway designed for those requiring universal offer support | ENF exists but a Universal ENF is required to plan for next steps for all CYP with EHCPs | Post 14 |  | SEND Transition Manager |  |  | 2023-12-01 |  |  | Children and young peoples needs will be planned resulting in smooth transitions Parents will have an understanding of the support available and be able to access that support |  | yes
|  |  | To promote the PFA transition events more widely using a range of media |  | To utilise current digital platforms such as Local Offer, Twitter, Education Hub and other communication mechanisms (newsletters, schools, preference forms) and partners (Our Voice, SENDIASS) to share information | Increased uptake in events attendance, feedback from partners, more young people are prepared for their next steps | SEND Newsletter is in development for parents to ensure that they are informed of the Transition Events. Newlsetters will be sent to schools and updated on the Local Offer. | Post 14 |  | SEND Transition Manager |  |  | 2024-01-01 |  |  | Children and young peoples and their families will be better prepared for their future and able to understand and access opportunities available to them. |  | no
|  |  | To have up to date advice information to ensure the EHCPs are reflective of current needs |  | To ensure all changes in needs (e.g. discharge notifications) are submitted timely prior to year 9 review so EHCPs are updated and reflect the current needs at time of transition | Health colleagues will provide SEN with timely reviewed advice which is captured as part of a robust monitoring process (including half termly reviews) |  | Post 14 |  | DCO |  |  | 2023-10-01 |  |  | All EHCPs will be updated with the latest required information and advice on how therapies will be delivered. Making sure that CYP will have their needs meet which will enable them to meet their identified learning outcomes. |  | yes
|  |  | To make sure families are aware of the step down offer from statutory service |  | Ensure Individual discharge reports at age 14-18 years provide a comprehensive overview of the low to moderate services offer available at 18+ | From March 24 0ngoing process for quality assurance checks of discharge reports by DCO and Heads of Service. |  | Post 14 |  | DCO |  |  | 2024-03-01 |  |  | CYP and families will understand the services available at age 18+ and have time to prepare for the transition period |  | yes
2.3 | Make sure all our children and young people receive an excellent education, and their needs are effectively met in an education setting or environment that is right for them. Wherever possible, this should be in a local mainstream setting. To support this, we are using our data and knowledge to accurately plan the right number of places, this includes increasing the number of Special Resourced Provisions (SRPs), and Designated Units in mainstream schools. |  |  | 2.3a | Review Schools Outreach Project to upskill staff in mainstream schools to meet more needs | Settings will be supported to provide special interventions/support for CYP with complex needs, who will be identified and supported and families will be porvided with interventions to meet the needs of their children. | An extended SLA has been given to exisiting special schools to provide support. A mapping and gapping exercise has been undertaken and a report will be prepared for the 2022 Schools Forum for deliberation and discussion on meeting identified gaps. | All phases | Education | Head of SEN and Curriculum Inclusion | SEN Advisor | Short-term | Summer 2023 |  | 1, 2, 3, 4 & 5 | Mainstream schools will benefit from advice and support from specialist settings in meeting the needs of CYP with SEN or additional needs. | Low | no
|  |  |  | 2.3b | Increase the number of ARPs | The number of ARPs has increased by 8 in the academic 2021/22. Improve place planning with Health to secure aligned health provision. | The new application process was set up, schools are now familiar and know how to apply. A multiagency panel was established to review applications and make timely decisions. A new review procedure and assessment procedure were also implemented. | All phases | Education | Head of SEN and Curriculum Inclusion | SEN Advisor | Long-term | On going |  | 1, 2, 3, 4 & 5 | Children can be educated locally and the inclusion agenda is fulfilled. | Low | no
|  |  |  | 2.3c | Increase the number of Units in primary schools to meet the needs of 120 children | The number of places in units has increased to 120 | 60 places achieved (July 2022) | Primary | Education | Head of SEN and Curriculum Inclusion | Lead Adviser (Education Safeguarding and Inclusion)​ | Long-term | On going |  | 1, 2, 3, 4 & 5 | Children are being inclusively educated within their locality and travel time and costs reduced | High | no
|  |  |  | 2.3d | Build a special school for CYP with Autism | 130 children are educated within Enfield | Decision has been agreed by Cabinet, DFE have approved the LA bid and a review of the provider is taking place | Primary | Education | Head of Strategic Resoucing & Partnerships Education | TBC | Long-term | 2026 |  | 1, 2, 3, 4 & 5 | Children are being inclusively educated within their locality and travel time and costs reduced | High | no
|  |  |  | 2.3e | Ensure we have a robust phase transfer processes in place that ensures CYP have the opportunity to be educated within Enfield | All children have a designated school by the February deadline, so that all children have a placement. | Phase process transfer is monitored annually and revised to reduce bureaucracy . A new PFA process has been agreed for 202324 academic year | All phases | Education | SEN Service Manager | SEN | Long-term | On going |  | 1, 2, 3, 4 & 5 | Children are being inclusively educated within their locality and travel time and costs reduced | High | no
2.4 | All educational settings to be confident and knowledgeable in identifying and meeting the needs of CYP with neurodiverse differences. Where learners with different strengths and needs can feel safe, understood and able to learn. |  |  | 2.4a | To develop early intervention models to meet the needs of children and families. | 1) There will be less referrals for statutory needs assessment. 2) Fewer requests for special school places. 3) Schools and families will inform us that they feel supported to address and meet the needs of their CYP. Align multi agency offers as part of the Neurodiversity pathway transformation project and NCL adhd-asd community services /Mental Health review for equity of access. | EASA has been expanded to provide early intervention and support to families and settings. There is a clear commitment set out in the Enfield Inclusion Charter Guidance (Enfield Council, 2022). Enfield's Ordinarily Available Provision document has been updated to include AET Good Autism Practice Principles (Enfield Council, 2022) and provides guidance on approaches they can use to tailor teaching and learning to the needs of different learners. | All phases | Education | Principle Educational Psychology and Strategic Mental Health Lead | Head of Enfield Advisory Service for Autism | Medium-term | Spring 2024 |  | 1, 2, 3, 4 & 5 | CYP will be supported when settings and parents identify that their children are not performing as they feel they should be. | Low | no
|  |  |  | 2.4b | To provide whole school support to children who are presenting with speech, language and communication challenges. Providing support to schools to enable them to idenitfy and be equipped with the tools they need to meet CYP needs. | Children's needs will be supported at an earlier stage to prevent them from becoming complex and requiring a neurodiverse assessment (and requiring a neurodiverse assessment) remove with evidence informed interventions at the point of concern taking equal or more importance than just a diagnosis. Seamless links to EASA and Health pathways are embedded throughout. | ECASS has been established to support CYP and their families with Speech, Language and Communications needs, to make sure that they are supported whilst awaiting NDA There is evidence of improved performance in 22 phonics | All phases | Education | Head of SEN and Curriculum Inclusion | ECASS Service Lead & Senior Specialist | Medium-term | Spring 2026 |  | 1, 2, 3, 4 & 5 | CYP will be supported to have their speech, language and communications needs identified and met at the earliest opportunity. | Low | no
2.5 |  | There are inconsistencies across education, health and social care in the way leaders share and use information about children and young people with SEND. | Make sure that our education, health and social care providers understand the importance of sharing and using current information and advice to make important decisions about a child/young persons next steps. | 2.5a | To raise the important of information sharing at the SEND Board, provide multi disciplinary IPSEA multi- training, relay the findings from quality assurance and ensure this is a key message at all partnership events. | Liquid Logic our CMS will be in place in 2024 where all information on the child will be stored in one place Attendance at IPSEA training Quality Assurance dip samples will review Section K information At statutory assessment all information requested will be utilised for the purpose of drafting the plan | IPSEA training had been commission and the 'Preparing a Legally Compliant EHC Plan' component is due to be delivered in January 2024. | All phases | All |  | SEND Improvement Lead | Medium-term | 2024-03-01 |  |  |  |  | no
2.6 |  | Leaders should ensure that children and young people with SEND who move from children to adult health services experience a smooth and effective transition. | Make sure our families are aware of transition events so they can plan their next steps as they move from children to adults services. This will include using various communication channels such as our Enfield Local Offer for SEND, the Parents and Carer forum (Our Voice), through informing educational settings (Education Hub) and by direct contact with families. | 2.6a | Engage with adult health services to ensure the current information is listed through our committment chanel. Review the way in which information is listed on the Enfield Local Offer for SEND and work with children, young people and families to make the appropriate changes/ | Increased uptake at events Increased traffic on Enfeild Local Offer for SEND More events advertisted in newsletters which will be included in correspondance with families | All information is published on the Local Offer. Newsletters will be published in the first academic term (23/24) with the list of upcoming events | Post 14 | All | SEN Improvement Lead |  | Medium-term | 2024-03-01 |  | 2,3,4,5 | Young people and their families will be aware of the transition pathways and their next steps as they move between adult health services. This will be supported by information explaining next steps, what to expect and how to access new opportunities. | medium | no
Note on H21: Suzy Francis: Can this be the other way round - x% are within 6 week time frame

## Priority 3
SEND Joint Local Area Action Plan
Priority 3: Make sure inclusion is at the heart of our services and communities | [9 empty] | RAG Rating: Blue: Action has been delivered Green: In delivery and timeline on track Amber: In delivery but delays / uncertainty over future delivery. Red: Work not yet commenced, budget not yet allocated and future delivery at risk or unknown. Impact: High - Significant impact on CYP outcomes or budget Medium – Moderate impact on CYP outcomes or budget Low - Limited impact on CYP outcomes or budget Timeframe (short-term/ medium-term/ long-term) Short-term - (delivery/ completion in under 1 year) Medium-term - (delivery/ completion within 1 - 3 years) Long-term - (delivery/ completion in 3 - 5 years) |  |  |  |  | Ofsted and CQC Proposed Inspection Outcomes (TBC live consultation) https://www.gov.uk/government/consultations/a-new-approach-to-area-send-inspections OIF 1: children and young people’s needs are identified accurately and assessed in a timely and effective way OIF 2: children, young people and their families participate in decision-making about their individual plans and support OIF 3: children and young people receive the right help at the right time OIF 4: children and young people are well prepared for their next steps, and achieve strong outcomes OIF 5: children and young people with SEND are valued, visible and included in their communities
Identified aims of the SEN Self Evaluation Framework (SEF):2. The Effectiveness of the Local Area in Assessing and Meeting the Needs of Children and Young People who have Special Educational Needs and/or Disabilities
Objective Code | Objective / Commitment 2022-26 | Post Area SEND Inspection: Area of Improvement & Judgement | Post Area SEND Inspection: Objective | Action Sub-Code | Actions | Measure/ SEN2 Indicator | Progress update | Education Phase | Education, Health or Social Care | Lead (name, title and org) | Delegated officer (delivery) | Timeframe (short- term/ medium-term/ long-term) | Deadline/ expected by | RAG Rating | Potential OIF Code Click here for more information | Impact | High, medium or Low Impact | Risk Register Listing
3.1 | Build our network of inclusive settings, schools and colleges that have signed up to and are living by the principles of the Inclusion Charter. |  |  | 3.1a | Support our schools to sign up and implement the inclusion charter. | 60% (TBC) number of schools will be signed up to the charter by 2024. | Inclusion Charter Launch on the 18th October.85% of schools have signed up to the charter and 50% of Early Years settings | All phases | Education | Lucy Nutt |  | medium-term | 2023-07-01 |  | 1,2,3,4, | Children and young people will be welcomed into schools and schools will be able to identify and support required adaptations. | Medium | no
|  |  |  | 3.1b | Provide Secondary schools with training and support around SEN so that transition to secondary is smoother and parents have a more positive experience. | More parents/carers will feel supported with their transition at secondary school. | We have had 2 secondary schools now have ARPs that provide particular support in Speech, Language and Communication. | Secondary | Education | Head of SEN and Curriculum Inclusion & Head of School and Early Years Improvement Service | SEN Advisor | medium-term | autumn 2023 |  | 2, 3, 4 & 5 | Children and parents will have a more positive experience as they start secondary school. | High | no
|  |  |  | 3.1c |  | Primary schools develop robust transition plans for children transferring from year 6 to year 7 of secondary school. | N/A | Primary | Education | Head of SEN and Curriculum Inclusion & Head of School and Early Years Improvement Service | SEN Advisor | medium-term | spring 2023 |  | 2, 3, 4 & 5 | Children and parents will feel supported as they go through the transition from primary to secondary school | High | no
|  |  |  | 3.1d |  | Reduce the number of children not attending secondary school due to EBSNA. | We have extended the ASU unit to provide support for children with EBSNA. EBSNA Parntership Development Group meets half termly. 2 session EBSNA training workshops are offered to schools, partners and parents/carers on a termly basis. | Secondary | Education | Principle Educational Psychology and Strategic Mental Health Lead | Educational Psychologist | medium-term | autumn 2023 |  | 3 & 5 | Children will have more positive experience of school and be able to achive their lifes potential | High | no
|  |  |  | 3.1e | Produce a well publicised map of services so that parents/carers understand the provision available to meet the needs of CYP | Service Map available to parents that gives them an understanding of local provision. | Exploratory work has begun and a map of services has been completed and is awaiting finalisation. | Early Years | Education, Health or Social Care | Early Years Team Manager | SEND Improvement Lead | medium-term | Autumn 24 |  |  | Parents will be able to make apporpriate decisions about the services they require. | Low | no
|  |  |  | 3.1f | Close the gap of the educational outcomes of children with SEND and those in mainstream schools | Improve Phonics attainment, Greater Depth and reading | First national key stage outcomes show a gap between acheivement of pupil with and without SEND. School sbeing challenged in the core conversation. Across the phases the gap seems stable from 2019 to 2022 | All phases | Education | Head of School Improvement | Head of Early SEN Early Years | medium-term | 2024-03-01 |  | 1,2,3,4, | Children with SEN will make required progress and have the opportunity to compete for employment and education places with their peers | Medium | no
|  |  |  | 3.1g | All schools need to be good or outstanding | Currently 92% of schools are graded good or outstanding | All special schools are now good or outstanding as of July 2022 - New School Improvement programme in place to suuport schools with SEF, Core work to one visit a term, Termly School Recategorisation meeting, support schools to prevent them from moving to RI | All phases | Education | Head of School and Early Years Improvement Service | Head of School and Early Years Improvement Service to add | Long-Term | Autumn23 |  | 1,2,3,4 | Children will have better outcomes and better experinces of school |  | no
|  |  |  | 3.1i | Improve workforce development to support the learning outcomes and needs of CYP with SEND. | Children/young people's needs will be met by staff who are knowledgeable and confident and have capacity to provide support | Inclusion charter published, ordinarily available provision published, ECASS launched, EASA expanded, ETIPSS being rolled out and SENCO forums. Head of service coffee morning provided monthly. Networks that support DSL, Mental Health Leads Network, Network for Downs Syndrome, training for TA's how to support pupils with SEND and ELSA training and support programme, Special School Outreach Programme, Toolkit with Inclusion Charter, EBSNA Training Programme Termly. | All phases | Education | Head of SEN and Curriculum Inclusion, Head of School and Early Years Improvement Service & Principle Educational Psychology and Strategic Mental Health Lead | SEN Advisor | medium-term | ongoing |  | 3, 4 & 5 | Children and young people will have their needs met by high quality staff | Medium | no
|  |  |  | 3.1k | Devise a tracking of outcomes for young people in college to improve outcomes | To monitor achievements and trend analysis to improve outcomes at post-16 | PFA tracking group in existance since 2022 | Post-16 | Education | SEN Service Manager | High Needs and Tracking Manager | medium-term | spring 2023 |  | 3, 4 & 5 | We will be better able to develop the curriculum and provide support at post-16 | Medium | no
|  |  |  | 3.1l | Develop pre-internships for young people so that more YP can access employment | Prepare young people for employment opportuntities | West Lea have developed a pre-internship supported by the local authority. This is well established and embedded and has been enhanced. There is now a pre-Internship offer in place. | Post-16 | Education | Head of Post 16 Provision |  | medium-term | spring 2023 |  | 3, 4 & 5 | Young people will have the opportunity to gain emploment | Medium | no
3.2 | Continue to further develop the range of play, leisure and social opportunities available in the community to support children and young people with SEND to maintain a healthy lifestyle and to make healthy and informed choices about their physical and mental health and emotional wellbeing. |  |  | 3.2a | Gain the views of parents, children and young people to identify activities needed in the borough | link to Health OT Leisure Programs post -OT interventions improving access to mainstream leisure offers so offers become integrated with clear signposting and stepping into a range of options | Contacted Leisure, provided more swimming and provided more sessions for parents and families. Received a grant of 10k and provided swimming sessions that are disability friendly and making sure that there are staff disability friendly. | All phases | Education/social Care | Head of Services for Disabled Children | SEND Transition Manager/ Children and Young People's OT Clinical Lead | medium-term | spring 2023 |  | 1,2,3,4 | Families will have more appropriate leisure facilities to support their needs. | Medium | no
3.3 | Support early years settings, schools, colleges and our partners to implement and embed trauma-informed practice in their day-to-day work. |  |  | 3.3a | The Enfield Trauma Informed Practice in Schools & Settings (ETIPSS) initiatives needs to continue to be delivered across schools and be rolled out to early years settings by securing additional funding. E-TIPSS roles out the ARC Framework to support trauma infomred practice delivery. | 1) Number of schools that have engaged with the programme (Central Briefings, ARC Training and Whole School Community Training/Implementation). 2) Number of partners who have attended the training. 3) Number of E-TIPSS Champions trained to support the sustainabilty and growth of the programme across Enfield. 4) E-TIPSS is included in Council strategy documents to support outcomes across the local area. | All special schools are now good or outstanding as of July 2022 | School Age at present | Education | Principle Educational Psychology and Strategic Mental Health Lead | Vacant | long-term | 2026 |  | 1, 3, 4, 5 | Schools are more inclusive , Reduction in exclusions, youth violence, restraint practice, use of isolation rooms. Attendance and attainment improves. | Medium | no
3.5 | Support young people with SEND to be ambitious; active and included members of their communities and to further their independence as they prepare for adulthood. This includes good quality work experience, apprenticeship opportunities and supported internships tailored to their personal interests and goals. |  |  | 3.5a | Develop a range of employment opportunities for YP, including the 3 ships - apprenticeships, internships, traineeships. | Number of people transitioning into employment. | Since 2018 we have had 190 supported interns. | Post-16 | Education | Head of Post 16 Provision & Head of SEN and Curriculum Inclusion | Head of Post 16 Provision | medium-term | ongoing |  | 3, 4 & 5 | YP will be independent to widen their opportunities and thrive. | medium | no
3.6 | Continue to deliver on our commitments as community leader and champion for children, employer, service provider and commissioner to create an inclusive Enfield as set out in our Fairer Enfield Policy. |  |  | 3.6a | Continue to promote inclusion, independence and advocacy, and employment opportunitities. | Children's rights will be promotoed and adhered to so that they have a voice and a position within the community that enables them to be asparational | The inclusion charter and ordinarily available provision has been developed. | All phases | All agencies | TBC | TBC | long-term | on going |  | 1, 2, 3, 4 & 5 | CYP and their families will be fully able to participate in their communities and voice their experiences and future goals. | medium | no
3.7 |  | Parents of some young people with the most complex needs are also concerned that options to take part in activities such as youth clubs narrow as young people get older. | Make sure that advices, reports and other relevant information is shared across education, health and social care to make sure children and young people’s support is planned and enables them to be fully included and supported by their local community. | 3.7a | Work with our providers and communities to match up our young peoples needs and available provision, making parents and families ware of these opportuntities | Increase uptake and awareess of currently avaiable provision | Summer projects attendance and feedback is currently being evaluated. The results will used to indentify fututre events | All phases | All agencies | Head of Youth Work and Develoment Unit/ SEN Improvement Lead |  | Long-Term | ongoing |  | 1,2,3,4 & 5 | CYP and their families will be fully able to participate in activities held in their communities | medium | no
|  |  | Support and encourage our communities to offer and advertise inclusive activities to enable our children, young people and their families to access local opportunities | 3.7b | Work with Our Voice and other local groups to idenfitfy, support and advertise inclusive opportuntities to enhance existing out of svchool opportunties | Increase in local activities delivered and accessed by children with EHCP's | Untilising ongoing discussions and information sharing opportunities to recognise gaps in the availability of activities | All phases | All agencies | Our Voice/ SEN Improvement Lead, |  | Long-Term | on-going |  | 1,2,3,4 & 5 | CYP and their families acitivies needs will be catered for in their local communities | Medium | no

## Priority 4
SEND Joint Local Area Action Plan
Priority 4: Education Health and Care needs assessments and plans (EHCPs) are on time, effective and produced to a high standard | [9 empty] | RAG Rating: Blue: Action has been delivered Green: In delivery and timeline on track Amber: In delivery but delays / uncertainty over future delivery. Red: Work not yet commenced, budget not yet allocated and future delivery at risk or unknown. Impact: High - Significant impact on CYP outcomes or budget Medium – Moderate impact on CYP outcomes or budget Low - Limited impact on CYP outcomes or budget Timeframe (short-term/ medium-term/ long-term) Short-term - (delivery/ completion in under 1 year) Medium-term - (delivery/ completion within 1 - 3 years) Long-term - (delivery/ completion in 3 - 5 years) |  |  |  |  | Ofsted and CQC Proposed Inspection Outcomes (TBC live consultation) https://www.gov.uk/government/consultations/a-new-approach-to-area-send-inspections OIF 1: children and young people’s needs are identified accurately and assessed in a timely and effective way OIF 2: children, young people and their families participate in decision-making about their individual plans and support OIF 3: children and young people receive the right help at the right time OIF 4: children and young people are well prepared for their next steps, and achieve strong outcomes OIF 5: children and young people with SEND are valued, visible and included in their communities
Identified aims of the SEN Self Evaluation Framework (SEF):
Objective Code | Objective / Commitment 2022-26 | Post Area SEND Inspection: Area of Improvement & Judgement | Post Area SEND Inspection: Objective | Action Sub-Code | Actions | Measure/ SEN2 Indicator / Evidence | Progress update | Education Phase | Education, Health or Social Care | Lead (name, title and org) | Delegated officer (delivery) | Timeframe (short- term/ medium-term/ long-term) | Deadline/ expected by | RAG Rating | Potential OIF Code Click here for more information | Impact | High, medium or Low Impact | Risk Register Listing
4.1 | Complete 95% or more of statutory EHC needs assessments on time. |  |  | 4.1a | To develop systems and processes to make sure decisions can be made in line with legislation. | EHC needs assessments will be made within 6 weeks and proposed plans will be within statutory timelines. | All statutory needs assessment decisions are currently made on time and at a rate of 97% | All phases | Education | SEN Service Manager | High Needs and Tracking Manager | long-term | Completed |  | 1, 2, 3, 4 & 5 | All EHCNA result in families receiving decisions on whether or not their child requires statutory support in timely. | High | No
4.2 | Produce 95% or more of EHCPs within the statutory 20-week timeframe without exceptions. |  |  | 4.1a | To develop systems and processes to make sure decisions can be made in line with legislation. | 95% of EHCPs will be proposed and issued within statutory timeframes. | SEN2 Return was at 97% against 20 week statutory time-lines. Performance has been 100% since March 2023 | All phases | Education | SEN Service Manager | High Needs and Tracking Manager | long-term | on going |  | 1, 2, 3, 4 & 5 | Children will be supported to have their needs met through an EHCP within the stautory timeframe | High | No
4.3 | Make sure every EHCP is meaningfully co-produced with the family; and the plan is easy to understand with a clear account of the child or young person's needs and aspirations, linked to the right services and support. |  |  | 4.3a | To produce quality EHCPs that are SMART and encourages the CYP to thrive. | All EHCPs are rated as green through the quality assurance process, and all advices templates ensure that advices are of a high standard. | Co-production meeting is offered to every family. Quality assurance framework in place to monitor content and outcomes within the plan. OFSTED in March 23 rated the new EHCPs as good. | All phases | Education | SEN Service Manager | SEN Statutory Assessment Team Leader | long-term | on going |  | 1, 2, 3, 4 & 5 | Every child will have a meaningful plan that sets out their needs, goals and outcomes. | High | No
|  |  |  | 4.3b | 40 % number of co-production meetings are attended. | A co-production meeting is offered to every family. | Meetings are offered but very few parents are attending the meetings. | All phases | Education | SEN Service Manager | SEN Statutory Assessment Team Leader | long-term | on going |  | 1, 2, 3, 4 & 5 | Parents and young people are fully involved in the construction of the EHCP. | High | Yes
|  |  |  | 4.3c | All agencies to produce advices that provide specification and quantification, and which are SMART. | All advices are SMART, specified and quantified. | EP have deveoped and embedded a robused and staged quality assurance framework. Health have a quality assurance framework. Schools produce advice on an agreed template with the LA. Training was given at the SENCO forum on advice and outcomes. September 2023 all partners need training on PFA outcomes. Discussion with DFE to acquire this training has taken place. | All phases | Education | SEN Service Manager | SEN Statutory Assessment Team Leader | long-term | on going |  | 1, 2, 3, 4 & 5 | All agencies produce high quality advice that is SMART and enables CYP to thrive | High | Yes
4.4 | Make sure every child and young person’s EHCP is of a high standard by continually reviewing and strengthening our quality assurance processes. | Information Sharing: Leaders should ensure that there is consistency in information being made available on the needs of Children and young people | Improve information sharing with associated professionals and ensure EHCPs are representative of current needs | 4.4a | To annually review the quality assurance process and make sure that officers are producing high quality plans which are signed off as green. Post Area SEND Inspection: To use the SEN existing quality framework to review feedback on any areas of improvement to the EHCP from professional advices. | That an annual review of the QA process takes place and relevant changes are made. Post Area SEND Inspection: Improvement in the quality of EHCPs evidenced through dip sampling reviews; parents would see their child supported and stretched as evidenced through feedback, surveys and focus groups; young people would feel included and supported to achieve their outcomes gained through coproduction and progress against their annual review. Assessment of current workforce understanding of the process and relevant training identified. | A QA Annual Review has been undertaken in 2021 and 2022 a final academic year QA process for 2022 needs completing with all relevant data. | All phases | Health / Education / Social Care | SEN Improvement Lead, Principal Educational Psychology and Strategic Mental Health Lead, DCO, DSCO | SEN Service Manager | Mid-term | 2023-03-01 |  | 1, 2, 3, 4 & 5 | There is a strategic overview of the operational offer and systems are revised to improve the quality of plans, so that CYP receive a meaningful plan. Post Area SEND Inspection: Better informed high quality EHPCs that meet the needs of our children and young people. Parents feel that the needs of their children are recognised and result in appropriate provision. Information can be used to inform our joint commissioning and service development. | High | NO
|  |  | To provide the SEN Team and education settings with up to date information on the current needs of the individual including a discharge notification from therapies and include information on step-down to universal | 4.4b | To provide the SEN Team and education settings with up to date information on the current needs of the individual including a discharge notification from therapies and include information on step-down to universal | Received timely advices that meets the statutory requirements of issuing and updating an EHCP and updating an Annual Review. Evidenced also by the Health and Educational Psychology Advice interface meetings (6 weeks) | Discharge notices are sent to SEN but this is not consistent and advices and not always updated into the EHCP. Sytems need to be strengthened through a list of cases returned to Therapies for agreement on current status. | All phases | Health / Education / Social Care | SEN Sevice Manager / Designated clinical Office (DCO) DSCO, SEN Improvement Lead |  | Mid-term | 2024-03-01 |  |  | EHCPs/Annual Reviews will be updated with timely accurate information. This will mean that CYP will have their needs met and experience smooth transition to adulthood with the right services to meet their associated learning outcomes. | High | yes
|  |  | Refine our systems to make sure we share relevant information and receive timely advices and prescribed outcomes from our education, health and social care providers. This will be supported through the use of a new Case Management System (CMS) | 4.4c | Implement the new Case Management System (Liquid Logic) and provide access across the partnership to make certain that all records are updated to the system to upload information to inform children and young peoples needs and prescribed outcomes. | By July 2024 all stakeholders across education, health and social care will be accessing the new CMS Portal. Comprehensive training programme delivered to all accessing the new CMS. | New case management system is underway and scoping and reference groups established, go live date planned for June 2024 | All phases | Health / Education / Social Care | Head of Inclusion & SEND |  | Mid-term | March 2024 (SFshould this be June 2024) |  |  | All updates will be uploaded onto one system so that SEN Officers and schools will have access to the latest assessments that will be required for EHCPs and Annual Reviews to support transition to another education setting. | High | no
|  |  | Improve information sharing, self management pathways and self referral opportunities | 4.4d | Add Enfield CYP MH services into the directory of services which supports the Enfield Local Offer | CYP MH services added to local offer by March 24 |  | All phases | Health / Education / Social Care | Enfield ICB CAHMS commissioning manager |  | Mid Term | Match 2024 |  |  | EHCP planners and reviewers will have access to all current information to make certain that children and young people achieve their prescribed outcomes. The system will be more efficient and allow responsible officers the opportunity to work on up to date information |  | mo
|  |  | Improve the information sharing interface between NCL specialist services such as GOSH and Whittington Health audiology and borough CYP community services | 4.4e | NCL ICB to conduct review of how specialist NCL services share information with place based health services ensuring CYP with EHCP and SEND are flagged and appropriate health information is shared across the system. | Review carried out by March 2024 and action plan developed | Picked up as a risk log at SEND Board where health will provide regular updates. This will also be picked up by Heads at the Heads of Service Strategic Leads meeting. | All phases | Health / Education / Social Care | DCO |  | Mid Term | 2024-03-01 |  |  | All EHCPs will be updated with the latest required information and advice on how therapies will be delivered. Making sure that CYP will have their needs meet which will enable them to meet their identified learning outcomes. |  | no
|  |  |  | 4.4f | Hold Enfield workshop to promote use of London Care Record across local CYP health services (London Care Record currently under development) | Workshop held Q4 22/23 |  | All phases | Health / Education / Social Care | DCO |  | Mid Term | 2024-03-01 |  |  | Enfield CYP services will know how to access London Care Records and have greater access to individual case information held by specialist service providers. |  | no
4.5 | Improve our Annual Review process in line with statutory timeframes and guidance. NOTE: post Ofsted this committment has been strengthened by an additonal committment to; Make sure every EHCP is informed by and acknowledges the advices received from other professionals | Annual Reviews: The partnership should ensure that EHCPs consistently reflect current needs in the prescribed outcomes for children and young people. They should ensure that the annual review process leads to EHCPs being updated in a timely way. | Children and young people have relevant and up to date EHCPs that include all their prescribed outcomes | 4.5a | Increase the number of annual reveiws that take place timely. Post Area SEND Inspection: To monitor the Annual Review tracker and Action Plan to ensure they are completed in a timely mannerTo monitor the Annual Review tracker and Action Plan to ensure they are completed in a timely manner | 70% of AR will take place within the year. Post Area SEND Inspection: Performance will be evidenced by the Annual Review tracker | Tracker commenced in October 22 and is updated regularly and shared at SEN operational meetings weekly. Performance is improving | All phases | Education | SEN Service Manager | High Needs and Tracking Manager | Short term | 2024-01-01 |  | 1, 2, 3, 4 & 5 | Children's needs and outcomes will be reviewed annually to ensure their needs are met in the right place, at the right time and by the right agency. Post Area SEND Inspection: All CYP have a current EHCP that reflects their current need and prescribed outcomes which will enable them to thrive and attain their ambitions. | High | no
|  |  |  | 4.5b | Reduce the backlog off historical annual reviews. | All historical annual reviews will take place annually. | The AR tracker records all outstanding AR and updates are sent to the teams for action. | All phases | Education | SEN Service Manager | SEN Review & Transfer Team Manager | long-term |  |  | 1, 2, 3, 4 & 5 | Children's needs and outcomes will be reviewed annually to ensure their needs are met in the right place, at the right time and by the right agency. | High | no
|  |  |  | 4.5c | All schools to provide AR paperwork on time. | 100% of schools to send in their AR paperwork on time. We will track schools on this process, relating to sharing this information on time. | 65% of Post 16 providers are not returning their advices on time. 35% of pre 14 schools are not returning their data. A list of schools to be provided and reminder letters sent to schools who do not send in their paperwork on time and remind them of their legislative duties. | All phases | Education | SEN Service Manager | SEN Review & Transfer Team Manager | long-term | on going |  | 1, 2, 3, 4 & 5 | AR will be recorded timely in line with the legislative framework. | High | yes
|  |  |  | 4.5d | All schools to receive training on the AR process. | Provide training on the AR process and the recent Devon judgement. | Some training has been provided to the SENCO forum. | All phases | Education | SEN Service Manager | SEN Review & Transfer Team Manager | long-term | on going |  | 1, 2, 3, 4 & 5 | Schools will be compliant to the legislation and CYP needs will be identifed timely. | High | no
|  |  |  | 4.5e | To co-produce the new PFA templates with young peopled and transfer all continuing learners onto the new template (reviewed against the London Change Programme) | Final PFA template reviewed against the London Change Programme, implemented across the SEN Service | Part of the trial of the new template with DFE, new template had been developed and designed for consultation is due to commence in the Autumn | Post 14 |  | SEN Improvement Lead |  | short term | 2023-10-01 |  |  | The new template will support the PFA ambition so that young people are channelled to explore relevant PFA themes that meet their ambitions. |  | yes
|  |  |  | 4.5f | Post 14 Annual Reviews will be prioritised for dip sampling against the SEN Quality Assurance Framework | Improvement in quality of EHCPs evidenced through dip sampling reviews; parents would see their child supported and stretched as evidenced through feedback, surveys and focus groups; young people would feel included and supported to achieve their outcomes gained through coproduction and progress against their annual review | Focus on Dip-sampling of PFA plans will commence in September 2023 | Post 14 | Edu/Health/Social care/SEN | SEN Service Manager |  | Long term | 2024-09-01 |  |  | This will mean that all CYP will have a high quality EHCP that reflects their needs and enables CYP to have services that meet the prescribed needs and outcomes |  | no
4.6 | Make sure all outcomes in the Annual Review are actioned and decisions to maintain, amend or cease an EHCP are made in a timely way. |  |  | 4.6a | SEN officers complete the MAC decisions in line with legislative framework. | Number of MAC decisions are made within the statutory timeline. | 3 teams are now responsible for the AR process and a new tracker is in place to monitor progress. | All phases | Education | SEN Service Manager | High Needs and Tracking Manager | long-term | on going |  | 1, 2, 3, 4 & 5 | Families will understand the status of thier EHCP. | High | no
4.7 | Develop our workforce to make sure they are fully trained and confident in EHCP processes and procedures. |  |  | 4.7a | To ensure staff are fully conversant in EHC process and understand how to apply for, administer and review an EHCP. | All schools understand the process of applying for an EHCP. | Training has been provided for schools through the SENCO forum. A Review of paperwork in 2023/24 academic year will take place with school reps and SEN | All phases | Education | SEN Service Manager | SEN Advisor | long-term | on going |  | 1, 2, 3, 4 & 5 | Young peoples needs will be met timely. | High | no
4.8 | Have mechanisms in place to make sure health practitioners and clinicians fully support the integrated EHC needs assessment process, providing information, advice, support and interventions to meet identified need within statutory / stated timescales |  |  | 4.8a | Statutory agencies to provide advice on time so that a quality EHCP can be produced. | All advices will be produced on time as set out in the tracker. | There is a Health action plan in place to address commissioning need. | All phases | Education | Head of SEN and Curriculum Inclusion; DCO,PEP | SEN Service Manager | long-term | on going |  | 1, 2, 3, 4 & 5 | A quality EHCP will be produced, EHCNA decisions will be undertaken from contributions from all relevant agencies. | High | yes
4.1 |  | Transition Pathways: Ensure there are effective transition pathways and processes in place from paediatric to adult services across acute, primary care and community health services including children and young people with complex needs and transition to continuing healthcare (CHC) / adult health provision | To increase understanding of transition process and available services for CYP and families | 4.10a | Enfield CYP health providers submit updated reports to LA Single Point of Access within SEND service until Liquid Logic is up and running | Increased uptake of referrals from health providers to the SPA |  | Post 14 | Education | DCO |  |  | 2024-03-01 | On track |  | All CYP will have current health advice that will support the development of the provision in section E&F of the EHCP |  | no
[5 empty] | Commission Our Voice Enfield to develop with partners and publish a phased 14-25 “Preparing for adulthood” support offer for parents and young people in line with national guidance and best practice (e.g. NICE and Burdett transition model) and promote via the Local Offer including a DOS for self-directed access to adult services | By March 24 Our Voice to publish a 14-25 preparing for adulthood handbook | 14-25 “Preparing for adulthood” has been created for discussion | Post 14 | Health/SEN | Director Our Voice/ Senior CYP Health Commissioning Manager |  |  | 2024-03-01 | On track |  | Continuity of provision and support for young people with SEND aged 18-25 |  | no
[5 empty] | Agreement to extend remit of Transition Implementation Group and Transition Operation Groups to facilitate transition to adult therapy services without need for new GP referral, where appropriate. | New protocol to be signed off by TIG and TOG and embedded within their terms of reference by Dec 23 |  | Post 14 | Health/SEN | CYP Community services via the TIG and TOG |  |  | 2024-03-01 | On track |  | Young people and their families feel supported, knowledgeable, empowered and receive a good experience of care when transitioning into adult services. |  | no
Note on O16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Advices are received, systematically there is an issue with recording information and updating plans
Note on O21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Annual Review Tracker in place, and performance is increasing weekly against set target

## Priority 5
SEND Joint Local Area Action Plan
Priority 5: Develop opportunities for children and young people with complex needs to have high aspirations; participate and thrive | [9 empty] | RAG Rating: Blue: Action has been delivered Green: In delivery and timeline on track Amber: In delivery but delays / uncertainty over future delivery. Red: Work not yet commenced, budget not yet allocated and future delivery at risk or unknown. Impact: High - Significant impact on CYP outcomes or budget Medium – Moderate impact on CYP outcomes or budget Low - Limited impact on CYP outcomes or budget Timeframe (short-term/ medium-term/ long-term) Short-term - (delivery/ completion in under 1 year) Medium-term - (delivery/ completion within 1 - 3 years) Long-term - (delivery/ completion in 3 - 5 years) |  |  |  |  | Ofsted and CQC Proposed Inspection Outcomes (TBC live consultation) https://www.gov.uk/government/consultations/a-new-approach-to-area-send-inspections OIF 1: children and young people’s needs are identified accurately and assessed in a timely and effective way OIF 2: children, young people and their families participate in decision-making about their individual plans and support OIF 3: children and young people receive the right help at the right time OIF 4: children and young people are well prepared for their next steps, and achieve strong outcomes OIF 5: children and young people with SEND are valued, visible and included in their communities
Identified aims of the SEN Self Evaluation Framework (SEF):
Objective Code | Objective / Commitment 2022-26 | Post Area SEND Inspection: Area of Improvement & Judgement | Post Area SEND Inspection: Objective | Action Sub-Code | Actions | Measure/ SEN2 Indicator | Progress update | Education Phase | Education, Health or Social Care | Lead (name, title and org) | Delegated officer (delivery) | Timeframe (short- term/ medium-term/ long-term) | Deadline/ expected by | RAG Rating | Potential OIF Code Click here for more information | Impact | High, medium or Low Impact | Risk Register Listing
5.1 | Work together with the North Central London, Integrated Care Partnership to make sure that our children and young people with learning disabilities and/or autism can grow up and remain living in their local community and close to their families |  |  | 5.1a | Work together with the North Central London, Integrated Care Partnership to make sure that our children and young people with learning disabilities and/or autism can grow up and remain living in their local community and close to their families | CETR processes are in place and are fully embedded within the system with attendance from relvant agencies. | CETRs Take place, The mechanism is not yet fully embedded into the service. | All | Education, Health & Social Care | NCL ICP | DCO | Medium Term | 2024-03-01 |  | 1,2,3,4 | Children and Young people with significant needs will have the right support for transition out of hospital or secondary services so that they can be supported to their next steps | Medium | yes
|  |  |  | 5.1b | The EPS swiftly responds to a schools request for Critical Incident Critical Incident support following a sad or traumatic event. The EPS will pdate the current critical incident response protocol and publish it with communications to stakeholders. | Critical Incident Response Protocol is in place. EPS provides a response within one day. | The Enfield EPS Critical Incident Response Protocol is sent to every school on a request being raised. EPS ensures that there is appropriate communication with other services (e.g. CAMHS). The EPS responds to an average of 10 events a year. CIR is being updated and will be re-launched. | All | Education | Principle Educational Psychology and Strategic Mental Health Lead | Educational Psychologist | long-term | 2024-03-01 |  | 1, 3 | This will ensure that settings are able to manage a critical incident response in a supported way and this will enable a whole setting approach to reframe incidents to support children and families | Medium | No
|  |  |  | 5.1c | Maintain a Dynamic Support Register (DSR) | A dynamic Risk Register is maintained with NCL-ICB | A Dynamic Risk Register is in place and it is well embedded within the system. Early Warning flags are acted upon for Amber rag rated cases through MDT intensive support packages | All | Education, Health & Social Care | Head of Children and Young People Strategic Commissioning NCL | CAMHS & Integrated Partnership Commissioning Manager | long-term | 2023-09-01 |  | 1, 2, 3, 4, | All children and young people will be prepared for their next steps with the right support | Medium | No
|  |  |  | 5.1d | Equip workforce across the SEND Partnership with the knowledge, skills and approaches they need to provide the right help for our children and young people with the most complex needs (inc. trauma informed practice, Positive Behaviour Support and effective responses to behaviours of concern that meet Restraint Reduction Network Standards) and Autism informed practices. | Partnership training is funded and delivered by an agreed training provider. Train the Trainer in place to sustain the approach. Evidence that the training is implemented in schools and through partner agencies. | Physical Intervention train the trainer in place with a clear process of refresher training being provided to staff - PRICE is the Enfield training provider and is BILD Accredited meeting RRN standards. Positive Behaviour Support training has been partially rolled out to Durants and Russet House Special Schools and relevant partners. Plan/funding needed to roll this out to all special schools, mainstream schools and partner agencies. E-TIPSS training is being rolled out across all schools. Fernhouse, Durants and Orchardside (PRU) have recieved whole school community training and are on the implementation programme. | All | Education, Health & Social Care | Head of Service for Disabled Children/Principle Educational Psychology and Strategic Mental Health Lead - To be discussed further | SEN Advisor | long-term | Summer 2024 |  | 1, 2, 3, 4, | All staff will be equipped to provide the correct knowledge and skills to meet the needs of children and young people and to prepare them for their next steps. | Medium | No
|  |  |  | 5.1e | Identify and develop local provision for our children and young people with complex needs who require placements with therapeutic intervention. | A range of opportunities exist to support young people transitioning from education to be as independent as possible. Overnight respite care to be developed within Enfield | A range of provision exists within the borough to support those with complex needs, this includes Barnet and Southgate College LLDD provision, Cheviots and ILDS offer (Vicky to expand) Equals employment opportunities and bespoke packages, such as those with Marcus and Marcus, A post 16 provision is being set up at Oak-Tree School | All | Social Care | Head of Service for Disabled Children/Head of Access to Resources Integrated Services | Head of Access to Resources Integrated Services | long-term | 2024-03-01 |  | 1,2,3,4 | Young people will be properly prepared for adulthood and will transition to the most appropriate next steps. | High | Yes
5.2 | Support our young people to access the right discrete and specialist learning pathway that meets their medical, learning, and social needs. |  |  | 5.2a | Make certain that there are clear pathways to enable children and young people to access learning and social care pathways. | A range of opportunities exist for CYP, a more focused development will take place through DBV in September 2023 | A well established Transition groups exists, managed by social care and annual events take place with stakeholders from all support agencies present. | All | Education, Health and Social Care | SEND Transition Manager | Head of SEND& Curriculum Inclusion, Head of Social Care/DCO |  | 2024-03-01 |  | 1,2,3,4 | Young people will make the most appropriate choices about their future and will have a range of choices and will have upto date information that will support them and families in their decision making | Medium | No
|  |  |  | 5.2b |  | Post is permanent and in place since December 2022 and team are managed to deliver to service objectives | SEN have developed a post 14 team to make certain that timely reviews, annual Health Checks and transition takes place with Adult and Health Services. | Post 14 | Education, Health and Social Care | SEN Service Manager | SEN Post 14 Team Lead | Short-term | 2023-01-01 |  | 1,2,3,4 | Young people will be prepared for transition at the right time and will have the right information to support them to make the best next steps. | Medium | No
|  |  |  | 5.2c |  | Set up a tracking process to monitor performance of transiton | A post 14 tracking process has been developed to make certain that young people are identified early for transition into Post compulsory education and training or social care opportunities | Post 14 | Education, Health and Social Care | SEN Service Manager | High Needs and Tracking Manager | Short-term | 2023-07-01 |  | 1,2,3,4 | This objective will ensure staff stay on track of young peoples needs and in turn young people will be well prepared for their next steps. | Medium | No
|  |  |  | 5.2d |  | There are a range of employment opportuniteis available. Service is involved with NDTI programme to quality assure post 14 Internships | Equals has a range of opportunities for young people and adults with social care needs. New Internships have been established and Pre-Internships | Post 14 | Education | Service Director ILDS and Mental Health; Head of Post 16 provision | Equals Employment & Therapies Service Manager |  | 2023-01-01 |  | 1,2,3,4 | Young people will be able to make appropriate employment choices and be valued and visible in their communities | Medium | No
5.3 | Further develop our approach to inclusively and meaningfully involving children and young people with complex needs in the decision-making and planning of their care, and in shaping the services and support they need and use. |  |  | 5.3a | Young people with complex needs are enabled to shape decisions about their future and services they want or need. Agree with the schools for them to delivier a transition week and projects to enable children with complex needs to sharing ideas and theiir views | Number of assemblies held Feedback from children and young people captured by the schools with the resulting information put onto our Local Offer | This will feed into the outcome framework currently being developed |  |  | Head of Service for Disabled Children | SEND Transition Manager/ SEN Improvement Lead | Medium Term | 2024-04-01 |  | 1,2,3,4 | Young people will have a voice to express what they want for their future and will be at the heart of their decision making. | Medium | yes
5.4 |  | Leaders should ensure that information sharing across education, health and care services leads to a more consistent understanding of current needs and supports transition for children and young people as they move from one provider to another. | Develop our adult social care and PFA pathways to make sure their is a hybrid offer for young people transitioning between education,health and social care | 5.4a | Equip workforce across the SEND Partnership with the knowledge, skills and approaches they need to provide the right help for our children and young people with the most complex needs (inc. trauma informed practice, Positive Behaviour Support and effective | Established pathway Recruit member of staff to support this work Staff attend PFA training | Put forward a request to DFE to request PFA outcomes training IPSEA training has been commissioned and will be delivered during the winter term (23/24) | All | All | PFA Transition Development Manager |  | Medium Term | 2024-04-01 |  | 1,2,3,4, | Young people will have the opportunity to attend provision that is more appropriate to their needs and aspirations | Medium | no